## Slide 1: IT Infrastructure Architecture
Infrastructure lifecycle
(chapter 15 - 16)
Infrastructure Building Blocks
and Concepts

## Slide 2: Introduction
The infrastructure lifecycle encompasses the following steps:
  Purchasing infrastructure and services
  Build-up, testing and go-live
  Maintaining the infrastructure
  Deploying applications
  Decommissioning the infrastructure

## Slide 3: Purchasing infrastructure and services

## Slide 4: Purchasing infrastructure and services
Most large-scale IT projects require procurement of hardware, software, or services
The purchase process entails:
  Determining what is needed
  Getting an offer
  Ordering
  Delivery
  Warranty
  Renewal

## Slide 5: Determine what is needed
Before any purchase can be made, it must be crystal clear what is actually needed
A Bill of Materials (BoM) is made that includes part numbers of all items
  If allowed by the purchasing rules, work with suppliers to get the BoM
Also a Statement of Work (SoW) is made
  A SoW describes what the supplier will do, apart from delivering the goods
  It must be clear from the start who does what
The supplier can have specific requirements, like:
  Is a loading dock available to deliver goods to the datacentre?
  Is the elevator large enough to lift the equipment to the final destination?

## Slide 6: Getting an offer
In a large organization, the lead time for the internal procurement process can be several weeks, or even longer
  Find a supplier
  Handle contract issues and/or to get signatures from management to formally place the order
  Procurement will try to get discounts
It typically takes four to eight weeks for the supplier to deliver the goods

## Slide 7: Choice of suppliers
Most organizations use preferred suppliers for standard purchases
Having a small number of preferred suppliers makes the purchase process easier
  Contracts are already in place
  Discounts can be negotiated because of large volume purchases
Organizations often choose for a predefined purchase policy for their software stack
  When possible all software is either purchased from preferred suppliers, or built based on technology from preferred suppliers

## Slide 8: Choice of suppliers
The alternative is using a best of breed policy
  Each component is chosen based on the best quality or the most comprehensive feature set
Combination also possible:
  A standard software stack for commodity components
  Best of breed products for highly specific tasks, that are close to the core business processes

## Slide 9: Choice of suppliers
With hardware, predefined choices are typically made as well
  For instance, a policy could be to buy all network equipment from Cisco and all servers from HP
  Easier management of support contracts
  When a hardware component fails, one telephone number to the supplier’s support desk is all it takes to start the repair process
  Limit the knowledge needed in the organization to manage components

## Slide 10: Choice of suppliers
Having preferred suppliers can lead to a vendor lock-in
  After some time, for practical reasons, it becomes unfeasible to change suppliers
  The resulting lack of competition can lead to
    A higher price level in the long run
    A decrease in service levels

## Slide 11: Bidding and tendering
Getting an offer may involve a formal bidding process, also known as tendering
In general, a bidding process comprises the following steps:
  RFI – Request for Information
    A large group of suppliers is asked to inform the purchase department if they are capable of providing the required goods or service

## Slide 12: Bidding and tendering
  Short list
    Based on the RFI responses, the purchase department creates a short list of suppliers
    Which are most likely to be able to deliver the goods for a good price and with good service?
  RFP – Request for Proposal
    Suppliers in the short list are requested to make a proposal for the delivery
  Questions and clarification
    Planned between the publication of the RFP and the supplier’s responses
    Suppliers are given the opportunity to ask questions about the RFP (in writing)

## Slide 13: Bidding and tendering
  Offer
    Suppliers provide the answers to the RFP
    Includes an initial offer
  Terms and conditions negotiations
    The purchase department starts negotiations with the suppliers that provided the best response to the RFP
  BAFO - Best and final offer
    Preferred suppliers make a final price and SoW
    This is their last chance to change the offer
  Award
    Based on the BAFO, the purchase department awards the supplier with the deal

## Slide 14: Ordering and delivery
Ordering
  Typically done by the purchasing department
  Because the delivery time is often weeks after the purchase order is placed, it makes sense to start ordering the goods as early as possible
Delivery
  Beware that the person that physically receives the goods, is not always the one formally accepting the delivery
  Before signing for delivery, check the boxes for any damage and check for completeness of the delivery
Warranty period
  During the warranty period, defects will be fixed without additional cost

## Slide 15: Renewal
When purchased goods are used for some time, they might need renewal
  Hardware is often used for five years before it is replaced
  Software typically has makor releases every few years
  Service contracts are also often agreed upon for a fixed number of years
Often a renewal of the hardware, software licenses, or service contracts leads to a new purchase process
Systems management should have a Life Cycle Management (LCM) process implemented to handle timely renewal

## Slide 16: Deploying the infrastructure

## Slide 17: Assembling the infrastructure
Infrastructure can be assembled using the following checklist:
  Build up the physical datacenter room
    Raised floors
    Uninterruptable power supply
    Cooling facilities
    Fire prevention and detection
    Physical security
  Install redundant power cabling

## Slide 18: Assembling the infrastructure
  Install racks
    Typically, separate racks are installed for network, storage, and compute components
    Check if the computer floor can still be opened (no racks placed on multiple tiles)
  Test the facilities:
    Test alarms that should respond to a power failure or heating, ventilating and air conditioning (HVAC) failure
    Perform a visual check of the facilities
    Ensure cables are properly fixed in the racks and labelled
    Measure the airflow, temperature, and humidity
    Test the physical security controls

## Slide 19: Assembling the infrastructure
  Install the server, networking, and storage hardware
    Ensure not too much equipment is placed in one rack to prevent:
      Racks from falling over
      Using too much power
      Obstructing cooling air flow
    Ensure:
      Cabling is properly installed and labelled
      Equipment can be sled out of the racks without damaging cabling
    Check if maintenance on a component can be done without interfering with the other components

## Slide 20: Assembling the infrastructure
  Allow for a burn-in period to ensure the equipment is not “dead on arrival” (DOA) or fails within the first day
    Switch the equipment off and on several times to see if it doesn’t break
  Check the power and cooling usage of the equipment

## Slide 21: Assembling the infrastructure
  Configure the infrastructure components
    Configure routers, switches, and storage LUNs
    Install virtualization and operating systems
    Configure DNS and NTP
    Configure security configurations like network zoning and firewalls
    Perform a basic test to check network connectivity and storage availability

## Slide 22: Assembling the infrastructure
  Install systems management tools
    Backup and recovery
    Monitoring
    Logging
    IDS/IPS
  Test systems management processes.
    Create incidents, create and handle changes, etc.
  Provide as-built documentation to the systems managers.
    Populate the Configuration Management Database (CMDB)

## Slide 23: Testing the infrastructure
After assembling the infrastructure, it should be tested
Each test type has a predefined scope:
  Functional tests
    Ensure the infrastructure delivers the required functionality
  Performance tests
    Load, stress, and endurance tests
    Prove the infrastructure has enough resources to run applications with the required performance
  Security tests
    Penetration tests and vulnerability scans
    Prove security controls are in place and are functioning as designed

## Slide 24: Testing the infrastructure
Availability of the infrastructure can be tested by:
  Physical actions
    Pulling cables from infrastructure components
    Unexpectedly rebooting machines
  A failover test, a fallback test and a disaster recovery test
  Testing backup and recovery processes and disaster recovery plans

## Slide 25: Test stages
System integration test
  The combination of components is tested including their interfaces
  A system integration test checks both functional and non-functional requirements
Fallback test
  Fallback from the main datacenter to the secondary datacenter is checked on a technical level
Migration test
  Ensures applications are installed without errors and data from previous systems can be migrated to the new system as designed

## Slide 26: Test stages
Acceptance test
  The final check of the delivered infrastructure
  Consists mainly of verifying that all tests are performed and that defects found in previous tests are either solved or accepted
  Leads to a discharge of the project for the delivery of the infrastructure

## Slide 27: Go live scenarios
Big Bang
  At a set time, the existing system is switched off and the new system is immediately put in production, possibly after a short data migration run.
Disadvantage:
  It may be impossible to roll back to the old system after the system is live for some time
  Downtime can occur when something goes wrong during the switchover

## Slide 28: Go live scenarios
Parallel changeover
  Both the new and the existing system run simultaneously for some time (typically weeks)
  Allows for testing the new system on both functionality and non-functional attributes
  Ensuring it works with live production data before switching off the existing system
  Switching back is possible at any time, minimizing risk
Disadvantage:
  The cost of maintaining both systems
  Possible extra work to keep both systems in sync
  Many system designs don’t allow running two systems in parallel, for instance, if the system has many data interfaces with other systems

## Slide 29: Go live scenarios
Phased changeover
  Individual components or functionalities of the existing system are taken over by the new system, one by one
  The changeover can be done gradually and controlled
Disadvantage:
  Can be costly, as many interfaces between the existing and the new system must be created and maintained
  New interfaces introduce new risk to the scenario
  The existing system must be kept online until the last component or functionality is moved to the new system

## Slide 30: Go live scenarios
The go-live should be very well prepared
A step-by-step plan must be created describing each step in detail
This plan must be reviewed, tested and improved multiple times
  Well in advance of the go-live date to eliminate possible surprises and to minimize risk
The scenario should include:
  Intermediate tests
  Multiple “go/no go” milestones
  A defined point of no return

## Slide 31: Go live scenarios
At the go-live date, high alert is needed from:
  The project team
  Systems managers
  Service desk
  Senior management
After the new system is live, on-site support should be available for some predefined time